## Master Deliverables Sheet
Deliverable / Task Name | Responsible Party | Supporting Party | Section / Scenario | Approach (Strategy Paragraph + Quarter) | Draft (Full Document + Quarter) | QMS-Ready (Controlled Document + Quarter) | Estimated Duration (weeks) | Dependencies | Risk – Time Slip / Scope Creep | Risk – Impact if Incorrect | Notes / Strategy Summary
510(k) Strategy & Predicate Mapping | Partner | Redefine | Section 2 – Integrator Pathway | Pre‑Partnership (Q4 2025) – outline submission route, predicates, SE rationale | Q2 2026 – full strategy doc incl. comparison tables and risk/benefit | Q1 2027 – controlled submission plan under Partner QMS | 16 | Initial device description; risk categories drafted | Medium | High
Biocompatibility Plan (Materials & Patient Contact) | Partner | Redefine | Section 2 – Integrator Pathway | Pre‑AAHKS (Q4 2025) – paragraph on materials & ISO 10993 endpoints | Q2 2026 – full test matrix & rationales | Q1 2027 – approved test protocols & final reports filed to DHF | 24 | Material selection finalized; risk assessment draft | High | High
Sterility Strategy & Validation (EtO/Steam/Other) | Partner | 3rd Party | Section 2 – Integrator Pathway | Before Partnership (Q4 2025) – approach & modality selection | Q3 2026 – validation plan & lab SOW | Q1 2027 – executed validation reports & certificates | 26 | Packaging concept; device materials & cleaning validated | High | High
Usability / Human Factors Plan (IEC 62366) | Redefine | Partner | Section 2 – Integrator Pathway | Pre‑AAHKS (Q4 2025) – HFE approach & intended users/use scenarios | Q2 2026 – formative protocols & risk‑linked use errors | Q4 2026 – summative protocol; Q2 2027 – final report | 28 | Intended use; UI prototypes; risk analysis draft | Medium | High
Verification & Validation Master Plan (V&V MP) | Redefine | Partner | Section 2 – Integrator Pathway | Before Partnership (Q4 2025) – define verification vs. validation scope | Q2 2026 – test protocols drafted & mapped to requirements | Q1 2027 – executed reports & requirement traceability closure | 24 | Design inputs; trace matrix; Risk Mgmt Plan | Medium | High
Risk Management File (ISO 14971) | Redefine | Partner | Section 2 – Integrator Pathway | Pre‑AAHKS (Q4 2025) – RMP outline & initial hazards | Q1 2026 – full hazard analysis, mitigations & linkage to V&V | Q4 2026 – controlled RMF with post‑market plan stub | 20 | Design inputs; preliminary architecture | Medium | High
Quality Management System Implementation (Core SOPs) | Redefine | 3rd Party | Section 3 – Independent Pathway | Q1 2026 – phased SOP rollout plan | Q2–Q3 2026 – SOP drafts (Design Control, Doc Control, CAPA, etc.) | Q4 2026 – internal audit ready | 32 | Org roles assigned; tooling picked (eQMS or manual) | High | High
Design Inputs & Traceability Matrix | Redefine | Partner | Section 3 – Independent Pathway | Q1 2026 – approach for reqs decomposition & numbering | Q2 2026 – full DI set & initial trace matrix | Q3 2026 – baselined DI & controlled TM | 16 | User needs; intended use; risk categories | Medium | High
Design Freeze (Baseline Configuration) | Redefine | Partner | Section 3 – Independent Pathway | Q2 2026 – freeze criteria & gate checklist | Q3 2026 – baseline BOM/CAD/specs | Q3 2026 – ECN baseline under Doc Control | 10 | Design inputs controlled; key risks mitigated | High | Medium
Electrical Safety & EMC Test Plan (60601 series) | Redefine | 3rd Party | Section 3 – Independent Pathway | Q1 2026 – test strategy & exclusions | Q2 2026 – lab SOW & pre‑compliance results | Q4 2026 – accredited test reports | 20 | Electrical architecture stable; risk controls defined | Medium | High
510(k) Submission Package (Full) | Partner | Redefine | Section 5 – Partner Submission Branch | Q3 2026 – content plan & template set | Q4 2026 – assembled modules & admin docs | Q1 2027 – final review & eCopy | 22 | V&V reports; biocomp; sterility; RMF; labeling | High | High
Independent Submission Readiness (Gap‑fill) | Redefine | 3rd Party | Section 5 – Independent Submission Branch | Q3 2026 – define gaps vs. partner path | Q4 2026 – generate missing tests/docs | Q2 2027 – internal submission‑ready | 26 | QMS implementation; V&V MP; risk file controlled | Medium | High
Supplier Controls & Incoming Inspection Plan | Partner | Redefine | Section 6 – Manufacturing & Post‑market | Q4 2026 – supplier qualification approach | Q1 2027 – inspection plans & quality agreements | Q2 2027 – approved & trained | 16 | Design freeze; drawing/specs released | Medium | High
Packaging & Shipping Validation (ISTA/ASTM) | 3rd Party | Partner | Section 6 – Manufacturing & Post‑market | Q4 2026 – approach & SOW | Q1 2027 – validation plan | Q2 2027 – test reports & certifications | 14 | Packaging design; labeling drafts | Medium | Medium
Labeling / IFU (Content & UDI) | Partner | Redefine | Section 6 – Manufacturing & Post‑market | Q4 2026 – labeling approach & UDI plan | Q1 2027 – full drafts & translations plan | Q2 2027 – controlled labeling & UDI assignment | 12 | Intended use; risk mitigations; HFE output | Medium | High
Mechanical / Bench Performance Testing | Redefine | 3rd Party | Section 6 – Manufacturing & Post‑market | Q4 2026 – define representative worst‑case | Q1 2027 – protocols & fixtures | Q2–Q3 2027 – executed reports | 18 | Design freeze; risk mitigations; DV samples available | Medium | High
Post‑market Surveillance Plan | Partner | Redefine | Section 6 – Manufacturing & Post‑market | Q2 2027 – PMS approach & sources | Q3 2027 – signal detection workflows | Q4 2027 – controlled PMS plan | 12 | Risk mgmt file; complaint handling SOP | Low | Medium

## Redefine Surgery
Deliverable / Task Name | Responsible Party | Supporting Party | Section / Scenario | Approach (Strategy Paragraph + Quarter) | Draft (Full Document + Quarter) | QMS-Ready (Controlled Document + Quarter) | Estimated Duration (weeks) | Dependencies | Risk – Time Slip / Scope Creep | Risk – Impact if Incorrect | Notes / Strategy Summary
Usability / Human Factors Plan (IEC 62366) | Redefine | Partner | Section 2 – Integrator Pathway | Pre‑AAHKS (Q4 2025) – HFE approach & intended users/use scenarios | Q2 2026 – formative protocols & risk‑linked use errors | Q4 2026 – summative protocol; Q2 2027 – final report | 28 | Intended use; UI prototypes; risk analysis draft | Medium | High
Verification & Validation Master Plan (V&V MP) | Redefine | Partner | Section 2 – Integrator Pathway | Before Partnership (Q4 2025) – define verification vs. validation scope | Q2 2026 – test protocols drafted & mapped to requirements | Q1 2027 – executed reports & requirement traceability closure | 24 | Design inputs; trace matrix; Risk Mgmt Plan | Medium | High
Risk Management File (ISO 14971) | Redefine | Partner | Section 2 – Integrator Pathway | Pre‑AAHKS (Q4 2025) – RMP outline & initial hazards | Q1 2026 – full hazard analysis, mitigations & linkage to V&V | Q4 2026 – controlled RMF with post‑market plan stub | 20 | Design inputs; preliminary architecture | Medium | High
Quality Management System Implementation (Core SOPs) | Redefine | 3rd Party | Section 3 – Independent Pathway | Q1 2026 – phased SOP rollout plan | Q2–Q3 2026 – SOP drafts (Design Control, Doc Control, CAPA, etc.) | Q4 2026 – internal audit ready | 32 | Org roles assigned; tooling picked (eQMS or manual) | High | High
Design Inputs & Traceability Matrix | Redefine | Partner | Section 3 – Independent Pathway | Q1 2026 – approach for reqs decomposition & numbering | Q2 2026 – full DI set & initial trace matrix | Q3 2026 – baselined DI & controlled TM | 16 | User needs; intended use; risk categories | Medium | High
Design Freeze (Baseline Configuration) | Redefine | Partner | Section 3 – Independent Pathway | Q2 2026 – freeze criteria & gate checklist | Q3 2026 – baseline BOM/CAD/specs | Q3 2026 – ECN baseline under Doc Control | 10 | Design inputs controlled; key risks mitigated | High | Medium
Electrical Safety & EMC Test Plan (60601 series) | Redefine | 3rd Party | Section 3 – Independent Pathway | Q1 2026 – test strategy & exclusions | Q2 2026 – lab SOW & pre‑compliance results | Q4 2026 – accredited test reports | 20 | Electrical architecture stable; risk controls defined | Medium | High
Independent Submission Readiness (Gap‑fill) | Redefine | 3rd Party | Section 5 – Independent Submission Branch | Q3 2026 – define gaps vs. partner path | Q4 2026 – generate missing tests/docs | Q2 2027 – internal submission‑ready | 26 | QMS implementation; V&V MP; risk file controlled | Medium | High
Mechanical / Bench Performance Testing | Redefine | 3rd Party | Section 6 – Manufacturing & Post‑market | Q4 2026 – define representative worst‑case | Q1 2027 – protocols & fixtures | Q2–Q3 2027 – executed reports | 18 | Design freeze; risk mitigations; DV samples available | Medium | High

## Partner
Deliverable / Task Name | Responsible Party | Supporting Party | Section / Scenario | Approach (Strategy Paragraph + Quarter) | Draft (Full Document + Quarter) | QMS-Ready (Controlled Document + Quarter) | Estimated Duration (weeks) | Dependencies | Risk – Time Slip / Scope Creep | Risk – Impact if Incorrect | Notes / Strategy Summary
510(k) Strategy & Predicate Mapping | Partner | Redefine | Section 2 – Integrator Pathway | Pre‑Partnership (Q4 2025) – outline submission route, predicates, SE rationale | Q2 2026 – full strategy doc incl. comparison tables and risk/benefit | Q1 2027 – controlled submission plan under Partner QMS | 16 | Initial device description; risk categories drafted | Medium | High
Biocompatibility Plan (Materials & Patient Contact) | Partner | Redefine | Section 2 – Integrator Pathway | Pre‑AAHKS (Q4 2025) – paragraph on materials & ISO 10993 endpoints | Q2 2026 – full test matrix & rationales | Q1 2027 – approved test protocols & final reports filed to DHF | 24 | Material selection finalized; risk assessment draft | High | High
Sterility Strategy & Validation (EtO/Steam/Other) | Partner | 3rd Party | Section 2 – Integrator Pathway | Before Partnership (Q4 2025) – approach & modality selection | Q3 2026 – validation plan & lab SOW | Q1 2027 – executed validation reports & certificates | 26 | Packaging concept; device materials & cleaning validated | High | High
510(k) Submission Package (Full) | Partner | Redefine | Section 5 – Partner Submission Branch | Q3 2026 – content plan & template set | Q4 2026 – assembled modules & admin docs | Q1 2027 – final review & eCopy | 22 | V&V reports; biocomp; sterility; RMF; labeling | High | High
Supplier Controls & Incoming Inspection Plan | Partner | Redefine | Section 6 – Manufacturing & Post‑market | Q4 2026 – supplier qualification approach | Q1 2027 – inspection plans & quality agreements | Q2 2027 – approved & trained | 16 | Design freeze; drawing/specs released | Medium | High
Labeling / IFU (Content & UDI) | Partner | Redefine | Section 6 – Manufacturing & Post‑market | Q4 2026 – labeling approach & UDI plan | Q1 2027 – full drafts & translations plan | Q2 2027 – controlled labeling & UDI assignment | 12 | Intended use; risk mitigations; HFE output | Medium | High
Post‑market Surveillance Plan | Partner | Redefine | Section 6 – Manufacturing & Post‑market | Q2 2027 – PMS approach & sources | Q3 2027 – signal detection workflows | Q4 2027 – controlled PMS plan | 12 | Risk mgmt file; complaint handling SOP | Low | Medium

## 3rd Party
Deliverable / Task Name | Responsible Party | Supporting Party | Section / Scenario | Approach (Strategy Paragraph + Quarter) | Draft (Full Document + Quarter) | QMS-Ready (Controlled Document + Quarter) | Estimated Duration (weeks) | Dependencies | Risk – Time Slip / Scope Creep | Risk – Impact if Incorrect | Notes / Strategy Summary
Packaging & Shipping Validation (ISTA/ASTM) | 3rd Party | Partner | Section 6 – Manufacturing & Post‑market | Q4 2026 – approach & SOW | Q1 2027 – validation plan | Q2 2027 – test reports & certifications | 14 | Packaging design; labeling drafts | Medium | Medium